## Instructions
ISO/IEC 27001:2022 Internal Audit — Audit Findings Register
Kohsar Digital Bank (KDB) — Phase 3 Deliverable
Purpose
This Audit Findings Register consolidates the results of the Phase 3 ISO/IEC 27001:2022 internal audit assessment of Kohsar Digital Bank (KDB). It provides a traceable record of the assessed clauses and Annex A controls, their finalized status, the basis for each assessment, and links to supporting entries in the Audit Evidence Log. The register includes the 26 assessment items covered by the Phase 3 assessment: 5 management-system clause/governance items, 20 Annex A controls (19 Applicable and 1 Not Applicable), and the internal KDB Governance & Risk Escalation Flow — Stage 3 SLA criterion. Only confirmed Nonconformities are counted as independent findings.
How to Use This Register
• Finding ID provides a unique identifier for each assessed item in the register. • Reference identifies the applicable ISO/IEC 27001:2022 clause, Annex A control, or documented KDB governance criterion. • Requirement / Control identifies the subject assessed. • Result records the finalized assessment status. • Severity is populated only for confirmed Nonconformities. All confirmed Nonconformities in this assessment are Minor; no Major Nonconformity was identified. • Rationale / Basis records the evidence-based reasoning supporting the assessment result. • Evidence Reference(s) links the assessment to the corresponding Evidence Log entry or entries. • Cross-Reference / Notes records cross-referenced evidence, documented limitations, or other relevant qualifications. Pending / Evidence Insufficient and Evidence-Criteria Conflict items are not treated as confirmed Nonconformities. Cross-referenced items are not double-counted in the independent Nonconformity total.
Severity Methodology
Major — absence or significant breakdown of a required ISMS/process, a widespread or systemic failure, or a failure materially affecting KDB’s ability to achieve intended information-security outcomes. Minor — an isolated or limited failure against an established requirement, where the relevant process/control exists and is generally implemented, but a specific instance does not conform. Observation / OFI — no demonstrated nonconformity, but evidence indicates a reasonable opportunity to improve effectiveness, consistency, or assurance. No Observation / OFI is recorded as a confirmed finding in this register. Conforms, Pending, and Cross-Referenced items do not receive a Major/Minor severity rating.
Final Assessment Summary
Independent Nonconformities: 6 confirmed, all Minor, 0 Major. Pending / Open Items: 8 fully Pending assessment items, plus the Pending HR-notification leg of A.6.5. The A.6.5 access-control leg is cross-referenced to A.5.15 and is not counted as an independent finding. Standing documented limitations and source-mapping discrepancies are recorded separately in the Legend & Limitations sheet and are not treated as findings unless the finalized assessment expressly identifies a confirmed Nonconformity.

## Findings Register
Finding ID | Reference | Requirement / Control | Result | Severity | Rationale / Basis | Evidence Reference(s) | Cross-Reference / Notes
F-01 | 5.2 | Information security policy | Conforms |  | The top-level Information Security Policy was reviewed and is approved by the Board / Executive Sponsor, consistent with the Policy-tier authority defined in the Policy Hierarchy. The evidence supports the tested Clause 5.2 policy requirement. | EL-01
F-02 | 5.3 | Organizational roles, responsibilities and authorities | Conforms |  | The Governance Charter and Decision Rights Matrix document roles, responsibilities, and decision rights, including policy approval, risk acceptance, and exception approval. The available evidence supports the tested requirement for assignment and communication of information-security responsibilities. | EL-02
F-03 | Escalation Flow — Stage 3 SLA | Governance & Risk Escalation Flow (internal KDB governance criterion) | Nonconformity | Minor | 6 of 8 sampled issues met the Stage 3 three-business-day SLA; 2 of 8 breached it by 2 and 4 days, with no documented exception. The escalation process and Stage 3 review function exist and operate in the majority of sampled instances; the identified breaches therefore support a Minor Nonconformity rather than a systemic failure. | EL-03
F-04 | 6.1.3 | Information security risk treatment | Pending / Evidence Insufficient |  | The SoA demonstrates the documented output of risk treatment through applicability, justification, owner, and evidence expectations for the in-scope controls. However, no objective evidence of the upstream risk assessment/risk treatment process itself was identified, so conformity cannot be inferred from the SoA’s existence alone. | EL-04
F-05 | 7.5 | Documented information | Pending / Evidence-Criteria Conflict |  | The available evidence cannot be conclusively tested against the applicable criterion because Task 9’s actual policy approvals use the CISO role, while the Governance Charter / Policy Hierarchy defines Board / GRC Lead / GRC Co-Lead approval tiers. No role equivalence has been established between these source vocabularies. | EL-05 | See governance/source-mapping discrepancy in Legend & Limitations
F-06 | 8.1 | Operational planning and control | Conforms — with documented evidence limitations |  | The aggregate assessment of the 19 Applicable Annex A controls provides sufficient evidence that KDB’s in-scope information-security operations are substantially planned and controlled. Seven controls conform and five have confirmed Minor Nonconformities; no Major Nonconformity was identified. Six controls remain Pending because available KDB sources do not establish sufficiently specific criteria or thresholds. These limitations do not, on their own, demonstrate a breakdown of operational planning and control. | EL-06 | Pending control-level items and the standing role-vocabulary discrepancy are recorded as limitations, not findings
F-07 | A.5.7 | Threat intelligence | Conforms |  | The available threat-intelligence evidence supports the stated control expectation. No gap was identified in the assessed evidence. | EL-07
F-08 | A.5.9 | Inventory of information and other associated assets | Nonconformity | Minor | Two non-current asset records lacked required classification information. The inventory process exists, and the identified gap is limited to the sampled records rather than demonstrating that the control is absent or systemically broken. | EL-08
F-09 | A.5.10 | Acceptable use of information and other associated assets | Conforms |  | The Acceptable Use Policy and personnel acknowledgment evidence were reviewed. The available evidence supports the control requirement. | EL-09
F-10 | A.5.15 | Access control | Nonconformity | Minor | Two termination-related de-provisioning tickets breached the Task 9 §3.2 24-hour revocation requirement by 5 and 7 days respectively, with no documented exceptions. A.5.15 remains the primary finding; the same evidence is cross-referenced to A.6.5 and is not double-counted. | EL-10 | Primary finding; A.6.5 access-control leg is cross-referenced and not counted independently
F-11 | A.5.19 | Information security in supplier relationships | Pending / Evidence Insufficient |  | Supplier records were reviewed, including risk-related information for sampled suppliers. Risk classification was not established for two non-current suppliers; therefore, the applicability of the annual high-risk supplier review requirement cannot be conclusively tested. | EL-11
F-12 | A.5.23 | Information security for use of cloud services | Conforms |  | Cloud configuration and shared-responsibility evidence were reviewed for the DR/backup cloud environment. The available evidence supports the stated cloud-security control expectations. | EL-12
F-13 | A.5.24 | Information security incident management planning and preparation | Conforms |  | Incident response planning and exercise records were reviewed. The evidence includes dated exercise records and participants. No KDB source establishes a required exercise cadence, so the observed interval is not treated as a nonconformity against an undefined requirement. | EL-13
F-14 | A.6.1 | Screening | Nonconformity | Minor | Background verification records were available for 8 of 10 sampled new hires; no record was identified for 2 of 10, against the SoA’s explicit evidence expectation. The record-keeping process exists, with the gap limited to the identified sample. | EL-14
F-15 | A.6.3 | Information security awareness, education and training | Pending / Evidence Insufficient |  | The Q2 2026 LMS completion report shows an overall completion rate of 87% across the in-scope population. No KDB source establishes a required completion-rate threshold or training cadence, so conformity or nonconformity cannot be concluded from the 87% figure alone. | EL-15
F-16 | A.6.5 | Responsibilities after termination or change of employment | Cross-Referenced (access leg) / Pending (HR-notification leg) |  | The access-control/de-provisioning leg uses the same two breached tickets evidenced under F-10 (A.5.15) and is not counted as an independent finding. The HR-notification leg remains Pending because no KDB source establishes a deadline for HR to issue the termination notification that starts the Task 9 §3.2 24-hour IT revocation clock. | EL-10 (cross-ref.), EL-16 | Primary finding is F-10; A.6.5 is not double-counted
F-17 | A.6.8 | Information security event reporting | Nonconformity | Minor | All 12 sampled events were reported through the designated channel and triaged. One Medium-severity event breached the 24-hour escalation requirement by 6 hours, with no exception filed. The separate 2-instance/90-day threshold for CISO/GRC Lead review was not reached; that threshold does not negate the individual escalation requirement. | EL-17
F-18 | A.7.1 | Physical security perimeters | Conforms |  | The perimeter security assessment report and access-controlled entry point diagram were reviewed and are consistent with the SoA’s justification. No further threshold is established in the available KDB sources. | EL-18
F-19 | A.7.4 | Physical security monitoring | Conforms |  | The CCTV retention log and Q2 2026 monitoring incident reports were reviewed and contain substantive content. The observed 30-day retention period is recorded as a simulated fact only and is not evaluated against a minimum requirement because no such KDB requirement is established. | EL-19
F-20 | A.7.7 | Clear desk and clear screen | Pending / Evidence Insufficient |  | Lahore and Karachi have Q2 2026 audit records, evidencing that the audit process is implemented and operating at those two locations. Islamabad has no current-year record identified. No KDB source defines the required frequency for “periodic” clear-desk audits, so the Islamabad gap cannot be conclusively assessed as a failure against an undefined threshold. | EL-20
F-21 | A.8.5 | Secure authentication | Conforms |  | MFA was enforced for the scenarios Task 9 §3.2 actually requires: remote access and Confidential/Restricted-tier systems. One documented exception had CISO approval. The Internal-tier HR system’s lack of MFA is not a gap because §3.2 does not require MFA for that tier. | EL-21
F-22 | A.8.8 | Management of technical vulnerabilities | Pending / Evidence Insufficient |  | The vulnerability scan report and patch dashboard exist. The 15-day Critical and 30-day High remediation targets shown in the dashboard are internally set figures, not established KDB-governed requirements; therefore conformity cannot be assessed against those self-set targets. | EL-22
F-23 | A.8.9 | Configuration management | Pending / Evidence Insufficient |  | Baseline documentation exists and drift detection is active on 85% of in-scope assets. No KDB source establishes a required drift-detection coverage threshold, so the 15% gap cannot be concluded as a nonconformity without inferring an unsupported completeness standard. | EL-23
F-24 | A.8.13 | Information backup | Pending / Evidence Insufficient |  | Backup job logs show 90 scheduled jobs, 88 successful and 2 failed before successful retry within 24 hours. One documented restore test was reviewed from Q1 2026. The SoA refers to “periodic” restore testing, but no KDB source defines the required frequency; therefore the available evidence cannot establish conformity or nonconformity on that point. | EL-24
F-25 | A.8.24 | Use of cryptography | Nonconformity | Minor | The cryptographic/key-management standard document required as SoA evidence is confirmed absent. However, the underlying encryption control is evidenced and operating for the systems tested: valid TLS certificates were confirmed on all 8 sampled customer-facing endpoints and cloud encryption-at-rest was enabled. The missing governance artifact is therefore treated as an isolated gap against an established evidence requirement rather than a systemic or absent control. | EL-25 | On-premises encryption-at-rest status is unknown and retained as an evidence limitation, not treated as evidence of absence
F-26 | A.8.30 | Outsourced development (Not Applicable) | Conforms (N/A exclusion verified) |  | The vendor/contract register and internal engineering organization chart were reviewed and are consistent with the SoA’s Not Applicable determination for outsourced development. This is a verification-of-exclusion conclusion, not a control-implementation test. | EL-26 | Vendor register evidence is shared with A.5.19; no duplicate finding is created

## Legend & Limitations
Color legend
Green fill — Conforms
Red fill — Nonconformity
Amber fill — Pending / Evidence Insufficient or Evidence-Criteria Conflict
Standing documented limitations / discrepancies (not findings)
1. SoA-owner vs. Task 9 Role-Vocabulary Mismatch — The Statement of Applicability (SoA) uses the roles SOC Manager, IT Asset Manager, IAM Lead, Third-Party Risk Manager, Incident Response Manager, Security Awareness Lead, and HR Manager. In contrast, KDB's actual Task 9 policies refer to CISO, IT Security Manager, Data Owner, Line Manager, Incident Response Lead, and Vendor Manager. No equivalence has been assumed between these role pairs at any point in this audit. This discrepancy affects the interpretation of Clauses 7.5 and 8.1 and is recorded as an evidence/source-mapping limitation for relevant control assessments. 2. Absent Physical & Environmental Security Policy — This policy is identified as an expected policy family in the SoA’s policy-family mapping but was not produced among Task 9’s five actual KDB policies. This absence does not translate into a nonconformity for A.7.1, A.7.4, or A.7.7, since none of those controls’ SoA evidence expectations necessitate the actual policy document. 3. A.8.24 On-Premises Database Encryption-at-Rest Status — The status of on-premises database encryption-at-rest remains unevidenced and is not confirmed absent. This point is strictly regarded as an evidence limitation on the A.8.24 finding, rather than as proof of encryption’s absence. 4. Clause 7.5 Governance Conflict — There exists a conflict involving KDB source documents, specifically the discrepancy between Task 9’s actual CISO approval practice and the Governance Charter / Policy Hierarchy approval tiers. This is identified as a conflict, not a confirmed nonconformity. No role equivalence has been inferred.